## Sheet1 (2)
Sr No. | Interface | Flow | Type | Task | Sub Task with priority | Development | Testing | Other | Person Day/Estimate | Status | Actual Person Day/Estimate | Start Date | End date | Comments
1 | Research | Discovery | Planned | Research the library. | 1. explore web3j. 2. undersatnding the web3 based flow. 3. Document the analysis. |  |  | 0.5 |  | New
2 | Exploration | Discovery | Planned | Exploring the smart contract. | 1. Finding the requirements for the smart contract. 2. Designing of the smart contract as alternate to traditional database along with proper edge cases. |  |  | 0.5 |  | New
3 | Implementation | Development | Planned | Implementing the smart contract. | 1. Writting the smart contract. 2. Testing the smart contract. 3. Deploying it to the ethereum testnet. | 1 | 0.3 |  |  | New
4 | Implementation | Development | Planned | Updating the API services | 1. Updating the sevice layer such that it would now interact with the Smart contract. 2. Testing the Services. | 1 | 0.5 |  |  | New
5 | Deployment | Development | Planned | Deploy the API | Deployment of the API service to Freebird VM. |  |  | 0.5 |  | New
6 | Demo | Demo | Planned | Demo (UI+ API + Blockchain)
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Total

## Sheet1
Sr No. | Interface | Flow | Type | Task | Sub Task with priority | Development | Testing | Other | Person Day/Estimate | Status | Actual Person Day/Estimate | Start Date | End date | Comments
1 | Research | Discovery | Planned | Research the library. | 1. explore web3j. 2. undersatnding the web3 based flow. 3. Document the analysis. |  |  | 0.5 |  | New
2 | Exploration | Discovery | Planned | Exploring the smart contract. | 1. Finding the requirements for the smart contract. 2. Designing of the smart contract as alternate to traditional database along with proper edge cases. |  |  | 0.5 |  | New
3 | Implementation | Development | Planned | Implementing the smart contract. | 1. Writting the smart contract. 2. Testing the smart contract. 3. Deploying it to the ethereum testnet. | 1 | 0.3 |  |  | New
4 | Implementation | Development | Planned | Updating the API services | 1. Updating the sevice layer such that it would now interact with the Smart contract. 2. Testing the Services. | 1 | 0.5 |  |  | New
5 | Deployment | Development | Planned | Deploy the API | Deployment of the API service to Freebird VM. |  |  | 0.5 |  | New
6 | Demo | Demo | Planned | Demo (UI+ API + Blockchain)
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Total